## Risk Chart
Severity
Probability |  | A | B | C | D | E
|  | Negligible | Low | Moderate | Severe | Catastrophic
5 | Nearly Certain | 0 | 0 | 0 | 0 | 0
4 | Likely | 0 | 1 | 0 | 1 | 0
3 | Possible | 0 | 0 | 0 | 0 | 0
2 | Unlikely | 0 | 0 | 2 | 1 | 0
1 | Rare | 0 | 1 | 1 | 4 | 1
Immediate Action
Urgent Action
Action
Monitor
No Action

## Risks
Risk | Probability | Severity | Date Identified | Mitigation | Progress | Notes | Action to Take | Numerical Severity
DJI SDK is an unsuitable development platform | 1 | C | 2015-10-02 |  |  | Cost risk | No Action | 3 | 1 | 5 | E | 0
Matrice cannot support our needs | 1 | D | 2015-10-02 | Research prior to purchase |  | Cost risk | Monitor | 4 | 2 | 4 | E | 0
Guidance sensors unsuitable to our requirements | 1 | D | 2015-10-02 |  |  | Schedule/cost risk | Monitor | 4 | 3 | 3 | E | 0
Simulations diverge significantly from reality | 2 | C | 2015-10-02 | Careful simulation creation |  | Schedule risk | Monitor | 3 | 4 | 2 | E | 0
Docking mechanism fails while Quadcopter is docking or docked | 4 | D | 2015-10-02 | Place net under platform |  | Physical risk | Immediate Action | 4 | 5 | 1 | E | 1
Quadcopter collision avoidance fails in flight | 2 | D | 2015-10-02 | Keep Guidance On |  | Physical risk | Action | 4 | 6 | 5 | D | 0
Quadcopter attempts to shut down engines after a false positive dock | 1 | D | 2015-10-02 | Place net under platform |  | Physical risk | Monitor | 4 | 7 | 4 | D | 1
Delays in shipping | 4 | B | 2015-10-02 | Order in advance |  | Schedule risk | Action | 2 | 8 | 3 | D | 0
NSH lab not big enough for testing | 1 | D | 2015-10-02 | Find that out early and reserve Rangos |  | Schedule Risk | Monitor | 4 | 9 | 2 | D | 1
Electrical failures | 2 | C | 2015-10-02 | Wire safety / fuses |  | Schedule/cost risk | Monitor | 3 | 10 | 1 | D | 4
Platform fails mechanical requirements | 1 | B |  | Make another one |  | Schedule risk | No Action | 2 | 11 | 5 | C | 0
A developer becomes unavailable | 1 | E |  |  |  | Schedule Risk | Monitor | 5 | 12 | 4 | C | 0
[7 empty] | #VALUE! | #VALUE! | 13 | 3 | C | 0
[7 empty] | #VALUE! | #VALUE! | 14 | 2 | C | 2
[7 empty] | #VALUE! | #VALUE! | 15 | 1 | C | 1
[7 empty] | #VALUE! | #VALUE! | 16 | 5 | B | 0
[7 empty] | #VALUE! | #VALUE! | 17 | 4 | B | 1
[7 empty] | #VALUE! | #VALUE! | 18 | 3 | B | 0
[7 empty] | #VALUE! | #VALUE! | 19 | 2 | B | 0
[7 empty] | #VALUE! | #VALUE! | 20 | 1 | B | 1
[7 empty] | #VALUE! | #VALUE! | 21 | 5 | A | 0
[7 empty] | #VALUE! | #VALUE! | 22 | 4 | A | 0
[7 empty] | #VALUE! | #VALUE! | 23 | 3 | A | 0
[7 empty] | #VALUE! | #VALUE! | 24 | 2 | A | 0
[7 empty] | #VALUE! | #VALUE! | 25 | 1 | A | 0
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!
[7 empty] | #VALUE! | #VALUE!